## Sheet1
Project: Quantify Server: dev.azure.com/cmput301w21t31 Query: Quantify Team - Stories List type: Tree
ID | Work Item Type | Title 1 | Title 2 | State | Story Points | Risk | Iteration Path | Tags | Priority
3 | User Story | US 01.01.01 - Publish an experiment |  | New | 3 | 2 - Medium | \Sprint 1 (Experiment) | owner | 1
4 | Task |  | Description | New |  |  | \ |  | 2
5 | Task |  | Region | New |  |  | \ |  | 2
6 | Task |  | Minimum number of trials | New |  |  | \ |  | 2
7 | User Story | US 01.02.01 - Unpublish an experiment |  | New | 1 | 3 - Low | \Sprint 1 (Experiment) | owner | 2
8 | User Story | US 01.03.01 - End an experiment |  | New | 2 | 3 - Low | \Sprint 1 (Experiment) | owner | 2
9 | User Story | US 01.04.01 - Subscribe to an experiment |  | New | 2 | 3 - Low | \Sprint 1 (Experiment) | experimenter; owner | 2
10 | User Story | US 01.05.01 - Execute trials and upload |  | New | 4 | 2 - Medium | \Sprint 1 (Experiment) | experimenter | 2
11 | Task |  | Execute trials for an experiment | New |  |  | \Sprint 1 (Experiment) |  | 2
12 | Task |  | Upload executed trials to the experiment | New |  |  | \Sprint 1 (Experiment) |  | 2
13 | User Story | US 01.06.01 - Histograms of results of trials |  | New | 5 | 3 - Low | \Sprint 1 (Experiment) | experimenter; owner | 3
14 | User Story | US 01.07.01 - Plots of the results of trials |  | New | 5 | 3 - Low | \Sprint 1 (Experiment) | experimenter; owner | 3
15 | User Story | US 01.08.01 - Ignore experimenters results |  | New | 1 | 3 - Low | \Sprint 1 (Experiment) | owner | 3
16 | User Story | US 01.09.01 - Observe statistics about current trials |  | New | 3 | 3 - Low | \Sprint 1 (Experiment) | experimenter; owner | 3
17 | Task |  | Observe quartiles | New |  |  | \Sprint 1 (Experiment) |  | 2
18 | Task |  | Observe median | New |  |  | \Sprint 1 (Experiment) |  | 2
19 | Task |  | Observe mean | New |  |  | \Sprint 1 (Experiment) |  | 2
20 | Task |  | Observe stdev | New |  |  | \Sprint 1 (Experiment) |  | 2
21 | User Story | US 02.01.01 - Ask a question about an experiment |  | New | 2 | 2 - Medium | \Sprint 2 (Questions and QR Codes) | experimenter | 2
22 | User Story | US 02.02.01 - Reply and require replies |  | New | 2 | 2 - Medium | \Sprint 2 (Questions and QR Codes) | experimenter; owner | 2
34 | Task |  | Reply to a question | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
35 | Task |  | Ask for reply（？） | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
23 | User Story | US 02.03.01 - Browse questions and replies |  | New | 1 | 3 - Low | \Sprint 2 (Questions and QR Codes) | experimenter; owner | 2
24 | User Story | US 03.01.01 - Generate QR codes |  | New | 4 | 3 - Low | \Sprint 2 (Questions and QR Codes) | experimenter | 2
26 | Task |  | QR for counts (how many did you see) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
27 | Task |  | QR for binomial trials (pass fail) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
28 | Task |  | QR for non-negative integer counts (each trial has 0 or more) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
29 | Task |  | QR for measurement trials (like the temperature) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
25 | User Story | US 03.02.01 - Scan QR codes |  | New | 5 | 3 - Low | \Sprint 2 (Questions and QR Codes) | experimenter | 2
30 | Task |  | Scan QR for counts (how many did you see) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
31 | Task |  | Scan QR for binomial trials (pass fail) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
32 | Task |  | Scan QR for non-negative integer counts (each trial has 0 or more) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
33 | Task |  | Scan QR for measurement trials (like the temperature) | New |  |  | \Sprint 2 (Questions and QR Codes) |  | 2
36 | User Story | US 03.03.01 - Register bar codes |  | New | 2 | 3 - Low | \Sprint 2 (Questions and QR Codes) | experimenter | 4
37 | User Story | US 04.01.01 - Add a profile |  | New | 2 | 2 - Medium | \Sprint 3 (User profile and Searching) | experimenter; owner | 2
38 | User Story | US 04.02.01 - Edit contact information |  | New | 1 | 2 - Medium | \Sprint 3 (User profile and Searching) | experimenter; owner | 2
39 | User Story | US 04.03.01 - Retrieve and show profile |  | New | 2 | 3 - Low | \Sprint 3 (User profile and Searching) | experimenter; owner | 2
40 | User Story | US 05.01.01 - Search experiments |  | New | 4 | 2 - Medium | \Sprint 3 (User profile and Searching) | experimenter | 2
41 | User Story | US 05.02.01 - Show search results |  | New | 2 | 3 - Low | \Sprint 3 (User profile and Searching) | experimenter | 2
42 | User Story | US 06.01.01 - Geo-location requirement on/off |  | New | 1 | 3 - Low | \Sprint 4 (Location) | owner | 2
43 | User Story | US 06.02.01 - Add Geo-location |  | New | 4 | 2 - Medium | \Sprint 4 (Location) | experimenter | 2
44 | User Story | US 06.03.01 - Warning on Geo-location requirements |  | New | 1 | 3 - Low | \Sprint 4 (Location) | experimenter | 4
45 | User Story | US 06.04.01 - Show a map of experiments |  | New | 3 | 3 - Low | \Sprint 4 (Location) | experimenter | 2

## VSTS_ValidationWS_1 (hidden)
value doesn't matter | value doesn't matter | value doesn't matter | value doesn't matter | \ | \ | Active | 1 | Active | 1 - High | 1 | Active | 1 - High | 1 | Active | 1 | Active | 1 | Closed | 1 | Active | 1 - High | 1 | Bug | Active | 1 | 1 - High | Active | 1 - High | 1 | Active
readOnlyTestRange_@ | readOnlyTestRange_0 | readOnlyTestRange_yyyy/M/d H:mm | readOnlyTestRange_General | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_System.AreaPath | \Sprint 1 (Experiment) | Closed | 2 | Closed | 2 - Medium | 2 | Closed | 2 - Medium | 2 | Closed | 2 | Closed | 2 | Design | 2 | Closed | 2 - Medium | 2 | Epic | Closed | 2 | 2 - Medium | Closed | 2 - Medium | 2 | Closed
[5 empty] | \Sprint 2 (Questions and QR Codes) | New | 3 | New | 3 - Low | 3 | New | 3 - Low | 3 | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Issue_System.State | 3 | New | 3 | Ready | 3 | New | 3 - Low | 3 | Feature | New | 3 | 3 - Low | New | 3 - Low | 3 | New
[5 empty] | \Sprint 3 (User profile and Searching) | Resolved | 4 | Removed | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Epic_Microsoft.VSTS.Common.Risk | 4 | Removed | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Feature_Microsoft.VSTS.Common.Risk | 4 |  | 4 | Removed | 4 | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Test Case_System.State | 4 | Removed | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_User Story_Microsoft.VSTS.Common.Risk | 4 | Issue | Resolved | 4 | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Microsoft.VSTS.Common.Risk | Removed | VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_D2-E2-6C-CC-CB-82-AA-DC-2F-1F-CB-87-84-07-EA-99-8C-32-EB-FE | 4 | Removed
[5 empty] | \Sprint 4 (Location) | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Bug_System.State | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Bug_Microsoft.VSTS.Common.Priority | Resolved |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Epic_Microsoft.VSTS.Common.Priority | Resolved |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Feature_Microsoft.VSTS.Common.Priority |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Issue_Microsoft.VSTS.Common.Priority | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Task_System.State | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Task_Microsoft.VSTS.Common.Priority |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Test Case_Microsoft.VSTS.Common.Priority | Resolved |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_User Story_Microsoft.VSTS.Common.Priority | Task | Removed | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Microsoft.VSTS.Common.Priority |  | Resolved |  | VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_A9-74-3C-60-20-83-BF-D2-70-44-DA-6E-AF-8C-55-96-9A-24-CE-B3 | VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_D9-65-6F-80-61-94-FF-9D-B2-07-9D-3A-AC-47-E7-8F-20-BA-F6-93
[5 empty] | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_System.IterationPath |  |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Epic_System.State |  |  | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_Feature_System.State | [8 empty] | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_User Story_System.State |  |  | Test Case | Design |  |  | VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_40-BC-AA-30-81-E2-8A-00-C4-6A-19-69-9D-98-4F-0C-87-30-E5-EC
[23 empty] | User Story | Ready
[23 empty] | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_System.WorkItemType | all_VSTS_5f9dce62_7214_463a_b41c_1402d1f2bc31_System.State